## Master Build Out ICU
ICU | TEAMS | BEDS | Potential Expansion into Different ICUs Based on Projections
|  | Patient Trigger | 2020-04-11 | 2020-04-18 | 2020-04-25 | 2020-05-02 | 2020-05-09 | 2020-05-16 | 2020-05-25 | 2020-06-01
MICU | A | 12
MICU | B | 24
MICU | C | 36
SICU | D | 48
SICU | E | 60
SICU | F | 72
Alternative ICU | G | 84
Alternative ICU | H | 96
Alternative ICU | I | 108

## April 11 - April 17
Tea
|  | MICU A = TRIGGER 1 | MICU B = TRIGGER 12 | MICU C = TRIGGER 24
|  | 12 Patients | 24 patients | 36 patients
| Attending | ICU Attending 1 |  | ICU Attending 2
| Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1
| Night Team Lead | CC Fellow 2 |  | Senior Resident 2
| Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3
| Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3
| ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3
| ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3
| Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3
| Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6

## April 18 - April 24
Team
|  | MICU A = TRIGGER 1 | MICU B = TRIGGER 12 | MICU C = TRIGGER 24
|  | 12 Patients | 24 patients | 36 patients
| Attending | ICU Attending 1 |  | ICU Attending 2
| Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1
| Night Team Lead | CC Fellow 2 |  | Senior Resident 2 | Back Up (need 1 at each level for each floor-- 30%)
| Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3 |  | MICU | SICU
| Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3 | Attending
| ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3 | Day Team Lead
| ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3 | Night Team Lead
| Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3 | Resident Day
| Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6 | Resident Night
NP Day
NP Night
Intern Day
Intern Day
|  | SICU D = TRIGGER 36 | SICU E = TRIGGER 48 | SICU F = TRIGGER 60
|  | 12 Patients | 24 patients | 36 patients
| Attending | ICU Attending 1 |  | ICU Attending 2
| Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1
| Night Team Lead | CC Fellow 2 |  | Senior Resident 2
| Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3
| Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3
| ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3
| ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3
| Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3
| Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6

## April 25 - May 1
| MICU A = TRIGGER 1 | MICU B = TRIGGER 12 | MICU C = TRIGGER 24
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1 | Back Up (need 1 at each level for each floor-- 30%)
Night Team Lead | CC Fellow 2 |  | Senior Resident 2 |  | MICU | SICU | ALT
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3 | Attending
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3 | Day Team Lead
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3 | Night Team Lead
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3 | Resident Day
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3 | Resident Night
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6 | NP Day
NP Night
Intern Day
| SICU D = TRIGGER 36 | SICU E = TRIGGER 48 | SICU F = TRIGGER 60 | Intern Day
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1
Night Team Lead | CC Fellow 2 |  | Senior Resident 2
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6
| ALT ICU G = TRIGGER 72 | ALT ICU H = TRIGGER 84 | ALT ICU I = TRIGGER 96
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1
Night Team Lead | CC Fellow 2 |  | Senior Resident 2
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6

## May 2 - May 8
| MICU A = TRIGGER 1 | MICU B = TRIGGER 12 | MICU C = TRIGGER 24
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1 | Back Up (need 1 at each level for each floor-- 30%)
Night Team Lead | CC Fellow 2 |  | Senior Resident 2 |  | MICU | SICU | ALT
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3 | Attending
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3 | Day Team Lead
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3 | Night Team Lead
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3 | Resident Day
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3 | Resident Night
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6 | NP Day
NP Night
Intern Day
| SICU D = TRIGGER 36 | SICU E = TRIGGER 48 | SICU F = TRIGGER 60 | Intern Day
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1
Night Team Lead | CC Fellow 2 |  | Senior Resident 2
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6
| ALT ICU G = TRIGGER 72 | ALT ICU H = TRIGGER 84 | ALT ICU I = TRIGGER 96
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1
Night Team Lead | CC Fellow 2 |  | Senior Resident 2
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6

## May 9 - May 15
| MICU A = TRIGGER 1 | MICU B = TRIGGER 12 | MICU C = TRIGGER 24
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1 | Back Up (need 1 at each level for each floor-- 30%)
Night Team Lead | CC Fellow 2 |  | Senior Resident 2 |  | MICU | SICU | ALT
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3 | Attending
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3 | Day Team Lead
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3 | Night Team Lead
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3 | Resident Day
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3 | Resident Night
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6 | NP Day
NP Night
Intern Day
| SICU D = TRIGGER 36 | SICU E = TRIGGER 48 | SICU F = TRIGGER 60 | Intern Day
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1
Night Team Lead | CC Fellow 2 |  | Senior Resident 2
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6
| ALT ICU G = TRIGGER 72 | ALT ICU H = TRIGGER 84 | ALT ICU I = TRIGGER 96
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1
Night Team Lead | CC Fellow 2 |  | Senior Resident 2
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6

## May 16 - May 22
| MICU A = TRIGGER 1 | MICU B = TRIGGER 12 | MICU C = TRIGGER 24
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1 | Back Up (need 1 at each level for each floor-- 30%)
Night Team Lead | CC Fellow 2 |  | Senior Resident 2 |  | MICU | SICU | ALT
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3 | Attending
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3 | Day Team Lead
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3 | Night Team Lead
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3 | Resident Day
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3 | Resident Night
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6 | NP Day
NP Night
Intern Day
| SICU D = TRIGGER 36 | SICU E = TRIGGER 48 | SICU F = TRIGGER 60 | Intern Day
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1
Night Team Lead | CC Fellow 2 |  | Senior Resident 2
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6
| ALT ICU G = TRIGGER 72 | ALT ICU H = TRIGGER 84 | ALT ICU I = TRIGGER 96
| 12 Patients | 24 patients | 36 patients
Attending | ICU Attending 1 |  | ICU Attending 2
Day Team Lead | CC Fellow 1 | ICU Attending Extender | Senior Resident 1
Night Team Lead | CC Fellow 2 |  | Senior Resident 2
Resident Day | Resident Day 1 | Resident Day 2 | Resident Day 3
Resident Night | Resident Night 1 | Resident Night 2 | Resident Night 3
ACNP Day | ACNP Day 1 | ACNP Day 2 | ACNP Day 3
ACNP Night | ACNP Night 1 | ACNP Night 2 | ACNP Night 3
Intern Day | Intern Day 1 | Intern Day 2 | Intern Day 3
Intern Day | Intern Day 4 | Intern Day 5 | Intern Day 6